## Backlog
Story ID | Story Name | Feature | Priority | Status | Persona | I Want | So That | Task Count | Sprint
F1-S1 | Project Structure & Configuration | F1: Foundation & Infrastructure | P0 | Backlog | Developer | a well-organized project with configuration management | I can develop with consistent patterns | 5
F1-S2 | Database Layer with PostgreSQL | F1: Foundation & Infrastructure | P0 | Backlog | Developer | async database access with connection pooling | I can persist incident and workflow data | 5
F1-S3 | MetIQ Enterprise AI Platform Integration | F1: Foundation & Infrastructure | P0 | Backlog | Developer | a unified LLM client integrated with MetIQ | agents can interact with the enterprise AI platform reliably | 6
F1-S4 | Embedding Client for Vector Search | F1: Foundation & Infrastructure | P0 | Backlog | Developer | to generate embeddings for semantic search | I can find similar incidents and known errors | 4
F1-S5 | Test Infrastructure | F1: Foundation & Infrastructure | P0 | Backlog | Developer | pytest configured with async support and fixtures | I can write reliable tests | 5
F2-S1 | Define Workflow State Schema | F2: LangGraph Workflow Engine | P0 | Backlog | Developer | a typed state schema for the workflow | all agents share a consistent data structure | 5
F2-S2 | Build Workflow Graph | F2: LangGraph Workflow Engine | P0 | Backlog | Developer | a LangGraph StateGraph that orchestrates the workflow | incidents flow through triage → diagnosis → remediation | 5
F2-S3 | Implement Routing Logic | F2: LangGraph Workflow Engine | P0 | Backlog | Developer | intelligent routing between workflow stages | incidents take the optimal path based on context | 5
F2-S4 | Workflow Runner with Tracing | F2: LangGraph Workflow Engine | P0 | Backlog | Developer | a high-level runner that processes incidents with tracing | I can track the complete incident lifecycle | 5
F3-S1 | Base Agent Framework | F3: Triage Agent | P0 | Backlog | Developer | a base agent class with common functionality | all agents share consistent patterns | 5
F3-S2 | Incident Deduplication | F3: Triage Agent | P0 | Backlog | Support Agent | to detect duplicate incidents | I reduce noise and prevent redundant processing | 5
F3-S3 | Error Classification | F3: Triage Agent | P0 | Backlog | Support Agent | to classify errors into categories | I can route to appropriate remediation | 5
F3-S4 | Correlation Analysis | F3: Triage Agent | P0 | Backlog | Support Agent | to identify related failures | I understand blast radius and root cause | 5
F3-S5 | Triage Agent Implementation | F3: Triage Agent | P0 | Backlog | Support Agent | to perform complete triage on incidents | they are classified, deduplicated, and routed correctly | 5
F4-S1 | Knowledge Retrieval (RAG) | F4: Diagnosis Agent | P0 | Backlog | Support Agent | to retrieve relevant knowledge before diagnosis | I can leverage past solutions | 7
F4-S2 | Hypothesis Generation | F4: Diagnosis Agent | P0 | Backlog | Support Agent | to generate diagnostic hypotheses | I can systematically investigate root cause | 4
F4-S3 | Evidence Gathering with Tools | F4: Diagnosis Agent | P0 | Backlog | Support Agent | to execute diagnostic tools to gather evidence | I can confirm or refute hypotheses | 4
F4-S4 | Root Cause Synthesis | F4: Diagnosis Agent | P0 | Backlog | Support Agent | to synthesize evidence into a root cause conclusion | I can propose appropriate remediation | 4
F4-S5 | Diagnosis Agent Implementation | F4: Diagnosis Agent | P0 | Backlog | Developer | a complete diagnosis agent | incidents are analyzed with AI-powered root cause analysis | 5
F5-S1 | Tool Base Classes | F5: Remediation Engine | P0 | Backlog | Developer | base classes for tools with rollback support | remediation actions are safe and reversible | 5
F5-S2 | Tool Registry | F5: Remediation Engine | P0 | Backlog | Developer | a registry for tool discovery | agents can find and use available tools | 5
F5-S3 | Rollback Manager | F5: Remediation Engine | P0 | Backlog | Developer | automatic rollback on failure | failed remediations don't leave systems in bad state | 5
F5-S4 | Proposal Agent | F5: Remediation Engine | P0 | Backlog | Support Agent | to generate remediation proposals | fixes can be reviewed before execution | 5
F5-S5 | Execution Agent | F5: Remediation Engine | P0 | Backlog | Support Agent | to execute approved remediation steps | issues are resolved automatically | 5
F5-S6 | Verification Agent | F5: Remediation Engine | P0 | Backlog | Support Agent | to verify that remediation worked | I don't close incidents prematurely | 5
F6-S1 | Provider Base Interface | F6: Provider System | P0 | Backlog | Developer | a plugin architecture for platforms | new platforms can be added without modifying core code | 5
F6-S2 | SQL Server Provider | F6: Provider System | P0 | Backlog | Platform Admin | SQL Server support | stored procedure failures are auto-remediated | 5
F6-S3 | SQL Server Diagnostic Tools | F6: Provider System | P0 | Backlog | Support Agent | diagnostic tools for SQL Server | I can gather evidence for root cause analysis | 0
F6-S4 | SQL Server Remediation Tools | F6: Provider System | P0 | Backlog | Support Agent | remediation tools for SQL Server | I can fix common issues automatically | 0
F7-S1 | Vector Store with Azure AI Search | F7: Knowledge Base & RAG | P1 | Backlog | Developer | vector storage for semantic search | I can find similar content by meaning | 5
F7-S2 | Known Error Database (KEDB) | F7: Knowledge Base & RAG | P1 | Backlog | Platform Admin | to store known errors with resolutions | the agent recognizes recurring issues | 5
F7-S3 | Incident History for Learning | F7: Knowledge Base & RAG | P1 | Backlog | Support Agent | to learn from resolved incidents | I improve over time | 4
F7-S4 | Howdy Integration for Historical Ticket Search | F7: Knowledge Base & RAG | P1 | Backlog | Support Agent | to search historical tickets via Howdy | I can leverage past resolutions from the enterprise ticket history | 8
F8-S1 | Structured Logging | F8: Observability | P1 | Backlog | Developer | structured JSON logging | logs are searchable and parseable | 4
F8-S2 | Prometheus Metrics | F8: Observability | P1 | Backlog | Platform Admin | Prometheus metrics | I can monitor system health | 4
F8-S3 | LangSmith Integration | F8: Observability | P1 | Backlog | Developer | LangSmith tracing for all LLM calls | I can debug and improve AI behavior | 5
F8-S4 | Audit Trail | F8: Observability | P1 | Backlog | Compliance Officer | an immutable audit log | all actions are traceable | 5
F9-S1 | FastAPI Application | F9: API & External Integration | P1 | Backlog | Developer | a production-ready API | external systems can submit incidents | 5
F9-S2 | Incident Endpoints | F9: API & External Integration | P1 | Backlog | Monitoring System | REST endpoints for incident management | I can submit and track incidents | 0
F9-S3 | Health & Metrics Endpoints | F9: API & External Integration | P1 | Backlog | Platform Admin | health check endpoints | Kubernetes can probe liveness/readiness | 0
F9-S4 | API Authentication | F9: API & External Integration | P1 | Backlog | Platform Admin | API key authentication | only authorized clients can access the API | 4
F9-S5 | Azure Service Bus Integration | F9: API & External Integration | P1 | Backlog | Platform Admin | to receive incidents via Service Bus | I can process messages asynchronously | 4
F9-S6 | SCSM ITSM Integration | F9: API & External Integration | P1 | Backlog | Developer | integration with Microsoft System Center Service Manager | the agent can query existing incidents and create new tickets | 7
F10-S1 | Approval Request System | F10: Human-in-the-Loop | P1 | Backlog | Support Agent | to request human approval for risky actions | humans maintain control | 4
F10-S2 | Approval API Endpoints | F10: Human-in-the-Loop | P1 | Backlog | Team Lead | API endpoints to approve/reject | I can authorize actions quickly | 0
F10-S3 | Auto-Approval Rules | F10: Human-in-the-Loop | P1 | Backlog | Platform Admin | to configure auto-approval for low-risk scenarios | simple fixes proceed without delay | 0
F11-S1 | Notification Channels | F11: Notifications & Escalation | P2 | Backlog | Platform Admin | to configure notification channels | the right people are alerted | 0
F11-S2 | Escalation Logic | F11: Notifications & Escalation | P2 | Backlog | Support Agent | to escalate when I cannot resolve | humans take over appropriately | 0
F11-S3 | Ticket Creation with SCSM | F11: Notifications & Escalation | P2 | Backlog | Support Agent | to create tickets in System Center Service Manager | escalated issues are tracked in the enterprise ITSM | 7
F12-S1 | Dashboard API | F12: Dashboard & Reporting | P2 | Backlog | Support Engineer | dashboard data endpoints | I can visualize incident status | 0
F12-S2 | Reporting Endpoints | F12: Dashboard & Reporting | P2 | Backlog | SRE Manager | reporting data | I can measure automation ROI | 0

## Tasks
Story ID | Story Name | Feature | Priority | Task # | Task Description | Status
F1-S1 | Project Structure & Configuration | F1 | P0 | 1 | Create directory structure: `src/`, `tests/`, `docs/`, `scripts/` | To Do
F1-S1 | Project Structure & Configuration | F1 | P0 | 2 | Set up `requirements.txt` with core dependencies | To Do
F1-S1 | Project Structure & Configuration | F1 | P0 | 3 | Create `src/integrations/config.py` with Pydantic Settings | To Do
F1-S1 | Project Structure & Configuration | F1 | P0 | 4 | Define environment variables in `.env.example` | To Do
F1-S1 | Project Structure & Configuration | F1 | P0 | 5 | Configure structlog for JSON logging | To Do
F1-S2 | Database Layer with PostgreSQL | F1 | P0 | 1 | Create `src/storage/database.py` with asyncpg pool | To Do
F1-S2 | Database Layer with PostgreSQL | F1 | P0 | 2 | Define SQLAlchemy models for core entities | To Do
F1-S2 | Database Layer with PostgreSQL | F1 | P0 | 3 | Set up Alembic migrations | To Do
F1-S2 | Database Layer with PostgreSQL | F1 | P0 | 4 | Implement repository pattern for data access | To Do
F1-S2 | Database Layer with PostgreSQL | F1 | P0 | 5 | Add health check for database connectivity | To Do
F1-S3 | MetIQ Enterprise AI Platform Integration | F1 | P0 | 1 | Create `src/integrations/llm_client.py` | To Do
F1-S3 | MetIQ Enterprise AI Platform Integration | F1 | P0 | 2 | Implement MetIQ client wrapper compatible with LangChain | To Do
F1-S3 | MetIQ Enterprise AI Platform Integration | F1 | P0 | 3 | Add exponential backoff retry (tenacity) | To Do
F1-S3 | MetIQ Enterprise AI Platform Integration | F1 | P0 | 4 | Support JSON mode for structured outputs | To Do
F1-S3 | MetIQ Enterprise AI Platform Integration | F1 | P0 | 5 | Track token usage for cost monitoring | To Do
F1-S3 | MetIQ Enterprise AI Platform Integration | F1 | P0 | 6 | Configure MetIQ endpoint and API authentication | To Do
F1-S4 | Embedding Client for Vector Search | F1 | P0 | 1 | Create `src/integrations/embedding_client.py` | To Do
F1-S4 | Embedding Client for Vector Search | F1 | P0 | 2 | Implement MetIQ embedding generation | To Do
F1-S4 | Embedding Client for Vector Search | F1 | P0 | 3 | Support batch embedding for efficiency | To Do
F1-S4 | Embedding Client for Vector Search | F1 | P0 | 4 | Cache embeddings to reduce API calls | To Do
F1-S5 | Test Infrastructure | F1 | P0 | 1 | Create `tests/conftest.py` with shared fixtures | To Do
F1-S5 | Test Infrastructure | F1 | P0 | 2 | Add `sample_incident` fixture | To Do
F1-S5 | Test Infrastructure | F1 | P0 | 3 | Add mock fixtures for LLM, vector store, database | To Do
F1-S5 | Test Infrastructure | F1 | P0 | 4 | Configure pytest-asyncio for async tests | To Do
F1-S5 | Test Infrastructure | F1 | P0 | 5 | Set up coverage reporting | To Do
F2-S1 | Define Workflow State Schema | F2 | P0 | 1 | Create `src/graph/state.py` | To Do
F2-S1 | Define Workflow State Schema | F2 | P0 | 2 | Define `AppSupportState` TypedDict | To Do
F2-S1 | Define Workflow State Schema | F2 | P0 | 3 | Create Pydantic models for nested structures | To Do
F2-S1 | Define Workflow State Schema | F2 | P0 | 4 | Define enums: `Severity`, `WorkflowStage`, `FailureCategory` | To Do
F2-S1 | Define Workflow State Schema | F2 | P0 | 5 | Implement `create_initial_state()` factory | To Do
F2-S2 | Build Workflow Graph | F2 | P0 | 1 | Create `src/graph/workflow.py` | To Do
F2-S2 | Build Workflow Graph | F2 | P0 | 2 | Define node functions for each workflow stage | To Do
F2-S2 | Build Workflow Graph | F2 | P0 | 3 | Implement routing functions for conditional edges | To Do
F2-S2 | Build Workflow Graph | F2 | P0 | 4 | Set up entry point and terminal nodes | To Do
F2-S2 | Build Workflow Graph | F2 | P0 | 5 | Add checkpointing for workflow persistence | To Do
F2-S3 | Implement Routing Logic | F2 | P0 | 1 | Implement `route_after_triage()` - routes based on classification | To Do
F2-S3 | Implement Routing Logic | F2 | P0 | 2 | Implement `route_after_diagnose()` - routes based on confidence | To Do
F2-S3 | Implement Routing Logic | F2 | P0 | 3 | Implement `route_after_proposal()` - routes based on risk level | To Do
F2-S3 | Implement Routing Logic | F2 | P0 | 4 | Implement `route_after_execution()` - handles success/failure | To Do
F2-S3 | Implement Routing Logic | F2 | P0 | 5 | Implement `route_after_verification()` - handles retry logic | To Do
F2-S4 | Workflow Runner with Tracing | F2 | P0 | 1 | Create `WorkflowRunner` class | To Do
F2-S4 | Workflow Runner with Tracing | F2 | P0 | 2 | Implement `process_incident()` method | To Do
F2-S4 | Workflow Runner with Tracing | F2 | P0 | 3 | Add LangSmith tracing wrapper | To Do
F2-S4 | Workflow Runner with Tracing | F2 | P0 | 4 | Implement `resume_workflow()` for paused workflows | To Do
F2-S4 | Workflow Runner with Tracing | F2 | P0 | 5 | Add metrics recording for workflow stages | To Do
F3-S1 | Base Agent Framework | F3 | P0 | 1 | Create `src/agents/base_agent.py` | To Do
F3-S1 | Base Agent Framework | F3 | P0 | 2 | Define `AgentConfig` for agent configuration | To Do
F3-S1 | Base Agent Framework | F3 | P0 | 3 | Implement `BaseAgent` with tool execution helpers | To Do
F3-S1 | Base Agent Framework | F3 | P0 | 4 | Add LLM interaction helpers (`chat_completion`, `chat_with_tools`) | To Do
F3-S1 | Base Agent Framework | F3 | P0 | 5 | Implement `__call__` for LangGraph compatibility | To Do
F3-S2 | Incident Deduplication | F3 | P0 | 1 | Create `src/intelligence/deduplication.py` | To Do
F3-S2 | Incident Deduplication | F3 | P0 | 2 | Implement exact duplicate detection (same job + error + time window) | To Do
F3-S2 | Incident Deduplication | F3 | P0 | 3 | Implement semantic duplicate detection (vector similarity) | To Do
F3-S2 | Incident Deduplication | F3 | P0 | 4 | Detect incident storms (>10 similar in 5 min) | To Do
F3-S2 | Incident Deduplication | F3 | P0 | 5 | Return `DeduplicationResult` with action and reason | To Do
F3-S3 | Error Classification | F3 | P0 | 1 | Create `src/intelligence/error_classification.py` | To Do
F3-S3 | Error Classification | F3 | P0 | 2 | Define rule-based patterns for known error codes | To Do
F3-S3 | Error Classification | F3 | P0 | 3 | Implement LLM-based classification for unknown errors | To Do
F3-S3 | Error Classification | F3 | P0 | 4 | Return classification with confidence score | To Do
F3-S3 | Error Classification | F3 | P0 | 5 | Map categories: `transient`, `resource`, `data`, `configuration`, `code` | To Do
F3-S4 | Correlation Analysis | F3 | P0 | 1 | Create `src/intelligence/correlation.py` | To Do
F3-S4 | Correlation Analysis | F3 | P0 | 2 | Implement temporal correlation (failures in time window) | To Do
F3-S4 | Correlation Analysis | F3 | P0 | 3 | Implement dependency correlation (upstream/downstream) | To Do
F3-S4 | Correlation Analysis | F3 | P0 | 4 | Implement infrastructure correlation (same cluster/server) | To Do
F3-S4 | Correlation Analysis | F3 | P0 | 5 | Return `CorrelationResult` with blast radius | To Do
F3-S5 | Triage Agent Implementation | F3 | P0 | 1 | Create `src/agents/triage_agent.py` | To Do
F3-S5 | Triage Agent Implementation | F3 | P0 | 2 | Integrate deduplication, classification, correlation | To Do
F3-S5 | Triage Agent Implementation | F3 | P0 | 3 | Implement knowledge retrieval for context | To Do
F3-S5 | Triage Agent Implementation | F3 | P0 | 4 | Calculate severity using multi-factor scoring | To Do
F3-S5 | Triage Agent Implementation | F3 | P0 | 5 | Generate routing decision | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 1 | Create `src/intelligence/knowledge_retrieval.py` | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 2 | Implement KEDB (Known Error Database) lookup | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 3 | Integrate Howdy for historical ticket search | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 4 | Implement similar incident search (vector similarity) | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 5 | Retrieve applicable runbooks | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 6 | Query recent changes/deployments from SCSM | To Do
F4-S1 | Knowledge Retrieval (RAG) | F4 | P0 | 7 | Parallel retrieval from all knowledge sources | To Do
F4-S2 | Hypothesis Generation | F4 | P0 | 1 | Add hypothesis generation to diagnosis agent | To Do
F4-S2 | Hypothesis Generation | F4 | P0 | 2 | Use LLM to generate 2-5 ranked hypotheses | To Do
F4-S2 | Hypothesis Generation | F4 | P0 | 3 | Each hypothesis includes: description, probability, evidence needed | To Do
F4-S2 | Hypothesis Generation | F4 | P0 | 4 | Map hypotheses to diagnostic tools | To Do
F4-S3 | Evidence Gathering with Tools | F4 | P0 | 1 | Create diagnostic tools (read-only) | To Do
F4-S3 | Evidence Gathering with Tools | F4 | P0 | 2 | Implement tool execution with timeout | To Do
F4-S3 | Evidence Gathering with Tools | F4 | P0 | 3 | Map tool results to hypotheses | To Do
F4-S3 | Evidence Gathering with Tools | F4 | P0 | 4 | Limit tool calls per diagnosis (max 5) | To Do
F4-S4 | Root Cause Synthesis | F4 | P0 | 1 | Implement evidence analysis with LLM | To Do
F4-S4 | Root Cause Synthesis | F4 | P0 | 2 | Generate root cause with confidence level | To Do
F4-S4 | Root Cause Synthesis | F4 | P0 | 3 | Include supporting evidence list | To Do
F4-S4 | Root Cause Synthesis | F4 | P0 | 4 | Recommend approach: auto-fix, manual, escalate | To Do
F4-S5 | Diagnosis Agent Implementation | F4 | P0 | 1 | Create `src/agents/diagnose_agent.py` | To Do
F4-S5 | Diagnosis Agent Implementation | F4 | P0 | 2 | Integrate knowledge retrieval | To Do
F4-S5 | Diagnosis Agent Implementation | F4 | P0 | 3 | Implement ReAct loop for hypothesis testing | To Do
F4-S5 | Diagnosis Agent Implementation | F4 | P0 | 4 | Generate diagnostic summary | To Do
F4-S5 | Diagnosis Agent Implementation | F4 | P0 | 5 | Handle low-confidence escalation | To Do
F5-S1 | Tool Base Classes | F5 | P0 | 1 | Create `src/tools/base.py` | To Do
F5-S1 | Tool Base Classes | F5 | P0 | 2 | Define `BaseTool` abstract class | To Do
F5-S1 | Tool Base Classes | F5 | P0 | 3 | Create `ReadOnlyTool` for diagnostics | To Do
F5-S1 | Tool Base Classes | F5 | P0 | 4 | Create `MutatingTool` with rollback support | To Do
F5-S1 | Tool Base Classes | F5 | P0 | 5 | Implement `ToolResult` with rollback info | To Do
F5-S2 | Tool Registry | F5 | P0 | 1 | Implement `ToolRegistry` class | To Do
F5-S2 | Tool Registry | F5 | P0 | 2 | Add `register()` and `get()` methods | To Do
F5-S2 | Tool Registry | F5 | P0 | 3 | Support category-based lookup | To Do
F5-S2 | Tool Registry | F5 | P0 | 4 | Generate tool schemas for LLM function calling | To Do
F5-S2 | Tool Registry | F5 | P0 | 5 | List read-only vs mutating tools | To Do
F5-S3 | Rollback Manager | F5 | P0 | 1 | Implement `RollbackManager` class | To Do
F5-S3 | Rollback Manager | F5 | P0 | 2 | Record executed actions on stack | To Do
F5-S3 | Rollback Manager | F5 | P0 | 3 | Implement `rollback_all()` in reverse order | To Do
F5-S3 | Rollback Manager | F5 | P0 | 4 | Implement `rollback_to(timestamp)` | To Do
F5-S3 | Rollback Manager | F5 | P0 | 5 | Handle rollback failures gracefully | To Do
F5-S4 | Proposal Agent | F5 | P0 | 1 | Create `src/agents/proposal_agent.py` | To Do
F5-S4 | Proposal Agent | F5 | P0 | 2 | Generate ordered remediation steps | To Do
F5-S4 | Proposal Agent | F5 | P0 | 3 | Assess risk level per step | To Do
F5-S4 | Proposal Agent | F5 | P0 | 4 | Calculate success probability | To Do
F5-S4 | Proposal Agent | F5 | P0 | 5 | Create rollback plan | To Do
F5-S5 | Execution Agent | F5 | P0 | 1 | Create `src/agents/execution_agent.py` | To Do
F5-S5 | Execution Agent | F5 | P0 | 2 | Execute steps sequentially with state capture | To Do
F5-S5 | Execution Agent | F5 | P0 | 3 | Stop on first failure | To Do
F5-S5 | Execution Agent | F5 | P0 | 4 | Trigger rollback on critical failures | To Do
F5-S5 | Execution Agent | F5 | P0 | 5 | Record execution metrics | To Do
F5-S6 | Verification Agent | F5 | P0 | 1 | Create `src/agents/verification_agent.py` | To Do
F5-S6 | Verification Agent | F5 | P0 | 2 | Define verification checks per action type | To Do
F5-S6 | Verification Agent | F5 | P0 | 3 | Implement verification with retry | To Do
F5-S6 | Verification Agent | F5 | P0 | 4 | Return verification evidence | To Do
F5-S6 | Verification Agent | F5 | P0 | 5 | Handle inconclusive results | To Do
F6-S1 | Provider Base Interface | F6 | P0 | 1 | Create `src/providers/base.py` | To Do
F6-S1 | Provider Base Interface | F6 | P0 | 2 | Define `BaseProvider` abstract class | To Do
F6-S1 | Provider Base Interface | F6 | P0 | 3 | Define `ProviderCapabilities` model | To Do
F6-S1 | Provider Base Interface | F6 | P0 | 4 | Implement `ProviderRegistry` for registration | To Do
F6-S1 | Provider Base Interface | F6 | P0 | 5 | Create decorator for registration | To Do
F6-S2 | SQL Server Provider | F6 | P0 | 1 | Create `src/providers/sql_server.py` | To Do
F6-S2 | SQL Server Provider | F6 | P0 | 2 | Implement connection management with pyodbc | To Do
F6-S2 | SQL Server Provider | F6 | P0 | 3 | Add diagnostic queries (deadlocks, blocking, stats) | To Do
F6-S2 | SQL Server Provider | F6 | P0 | 4 | Implement remediation actions | To Do
F6-S2 | SQL Server Provider | F6 | P0 | 5 | Define error patterns for SQL Server | To Do
F7-S1 | Vector Store with Azure AI Search | F7 | P1 | 1 | Create `src/storage/vector_store.py` | To Do
F7-S1 | Vector Store with Azure AI Search | F7 | P1 | 2 | Integrate Azure AI Search with vector index | To Do
F7-S1 | Vector Store with Azure AI Search | F7 | P1 | 3 | Implement hybrid search (vector + keyword) | To Do
F7-S1 | Vector Store with Azure AI Search | F7 | P1 | 4 | Support batch indexing | To Do
F7-S1 | Vector Store with Azure AI Search | F7 | P1 | 5 | Implement similarity threshold filtering | To Do
F7-S2 | Known Error Database (KEDB) | F7 | P1 | 1 | Define KEDB schema | To Do
F7-S2 | Known Error Database (KEDB) | F7 | P1 | 2 | Implement CRUD operations | To Do
F7-S2 | Known Error Database (KEDB) | F7 | P1 | 3 | Generate embeddings on create/update | To Do
F7-S2 | Known Error Database (KEDB) | F7 | P1 | 4 | Support regex patterns for matching | To Do
F7-S2 | Known Error Database (KEDB) | F7 | P1 | 5 | Track match statistics | To Do
F7-S3 | Incident History for Learning | F7 | P1 | 1 | Store resolved incidents with embeddings | To Do
F7-S3 | Incident History for Learning | F7 | P1 | 2 | Track resolution steps taken | To Do
F7-S3 | Incident History for Learning | F7 | P1 | 3 | Enable similarity search on past incidents | To Do
F7-S3 | Incident History for Learning | F7 | P1 | 4 | Flag successful resolutions for KEDB candidates | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 1 | Create `src/integrations/howdy_client.py` | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 2 | Implement Howdy API authentication | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 3 | Search historical tickets by error message/description | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 4 | Retrieve ticket details including resolution steps | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 5 | Parse and structure Howdy responses for agent consumption | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 6 | Cache frequently accessed tickets | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 7 | Handle Howdy API rate limits and errors | To Do
F7-S4 | Howdy Integration for Historical Ticket Search | F7 | P1 | 8 | Health check for Howdy connectivity | To Do
F8-S1 | Structured Logging | F8 | P1 | 1 | Configure structlog with JSON output | To Do
F8-S1 | Structured Logging | F8 | P1 | 2 | Add correlation IDs to all logs | To Do
F8-S1 | Structured Logging | F8 | P1 | 3 | Bind context (incident_id, agent, stage) | To Do
F8-S1 | Structured Logging | F8 | P1 | 4 | Configure log levels per environment | To Do
F8-S2 | Prometheus Metrics | F8 | P1 | 1 | Create `src/observability/metrics.py` | To Do
F8-S2 | Prometheus Metrics | F8 | P1 | 2 | Define key metrics (counters, histograms, gauges) | To Do
F8-S2 | Prometheus Metrics | F8 | P1 | 3 | Expose `/metrics` endpoint | To Do
F8-S2 | Prometheus Metrics | F8 | P1 | 4 | Create Grafana dashboard | To Do
F8-S3 | LangSmith Integration | F8 | P1 | 1 | Create `src/observability/langsmith_integration.py` | To Do
F8-S3 | LangSmith Integration | F8 | P1 | 2 | Wrap all LLM calls with traces | To Do
F8-S3 | LangSmith Integration | F8 | P1 | 3 | Add custom metadata (incident_id, stage) | To Do
F8-S3 | LangSmith Integration | F8 | P1 | 4 | Record feedback for learning | To Do
F8-S3 | LangSmith Integration | F8 | P1 | 5 | Create datasets from production traces | To Do
F8-S4 | Audit Trail | F8 | P1 | 1 | Create `src/observability/audit.py` | To Do
F8-S4 | Audit Trail | F8 | P1 | 2 | Define audit event types | To Do
F8-S4 | Audit Trail | F8 | P1 | 3 | Log all state changes | To Do
F8-S4 | Audit Trail | F8 | P1 | 4 | Log all tool executions | To Do
F8-S4 | Audit Trail | F8 | P1 | 5 | Support audit queries by incident | To Do
F9-S1 | FastAPI Application | F9 | P1 | 1 | Create `src/api/main.py` with FastAPI | To Do
F9-S1 | FastAPI Application | F9 | P1 | 2 | Add CORS middleware | To Do
F9-S1 | FastAPI Application | F9 | P1 | 3 | Add rate limiting | To Do
F9-S1 | FastAPI Application | F9 | P1 | 4 | Add request/response logging | To Do
F9-S1 | FastAPI Application | F9 | P1 | 5 | Configure graceful shutdown | To Do
F9-S4 | API Authentication | F9 | P1 | 1 | Implement API key validation | To Do
F9-S4 | API Authentication | F9 | P1 | 2 | Use constant-time comparison | To Do
F9-S4 | API Authentication | F9 | P1 | 3 | Support multiple API keys | To Do
F9-S4 | API Authentication | F9 | P1 | 4 | Log authentication events | To Do
F9-S5 | Azure Service Bus Integration | F9 | P1 | 1 | Create Service Bus listener | To Do
F9-S5 | Azure Service Bus Integration | F9 | P1 | 2 | Handle message deserialization | To Do
F9-S5 | Azure Service Bus Integration | F9 | P1 | 3 | Implement retry with dead-letter queue | To Do
F9-S5 | Azure Service Bus Integration | F9 | P1 | 4 | Add message deduplication | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 1 | Create `src/integrations/scsm_client.py` | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 2 | Implement authentication (Windows/NTLM or API key) | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 3 | Query recent incidents for correlation | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 4 | Query recent changes for root cause analysis | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 5 | Create work items for escalated incidents | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 6 | Update work item status on resolution | To Do
F9-S6 | SCSM ITSM Integration | F9 | P1 | 7 | Health check for SCSM connectivity | To Do
F10-S1 | Approval Request System | F10 | P1 | 1 | Define approval-required conditions | To Do
F10-S1 | Approval Request System | F10 | P1 | 2 | Store pending approvals in database | To Do
F10-S1 | Approval Request System | F10 | P1 | 3 | Implement timeout handling | To Do
F10-S1 | Approval Request System | F10 | P1 | 4 | Track approval decisions | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 1 | Create `src/integrations/scsm_client.py` | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 2 | Implement SCSM REST API / SDK integration | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 3 | Map incident data to SCSM work item schema | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 4 | Include diagnosis summary in work item description | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 5 | Link SCSM ticket ID to Support Agent incident | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 6 | Implement bi-directional status sync | To Do
F11-S3 | Ticket Creation with SCSM | F11 | P2 | 7 | Handle SCSM connection failures gracefully | To Do

## Features
Feature ID | Feature Name | Priority | Story Count | Task Count | Status
F1 | Foundation & Infrastructure | P0 | 5 | 25 | Backlog
F2 | LangGraph Workflow Engine | P0 | 4 | 20 | Backlog
F3 | Triage Agent | P0 | 5 | 25 | Backlog
F4 | Diagnosis Agent | P0 | 5 | 24 | Backlog
F5 | Remediation Engine | P0 | 6 | 30 | Backlog
F6 | Provider System | P0 | 4 | 10 | Backlog
F7 | Knowledge Base & RAG | P1 | 4 | 22 | Backlog
F8 | Observability | P1 | 4 | 18 | Backlog
F9 | API & External Integration | P1 | 6 | 20 | Backlog
F10 | Human-in-the-Loop | P1 | 3 | 4 | Backlog
F11 | Notifications & Escalation | P2 | 3 | 7 | Backlog
F12 | Dashboard & Reporting | P2 | 2 | 0 | Backlog
TOTAL |  |  | 51 | 205

## Sprint Planning
Sprint | Feature | Story ID | Story Name | Priority | Complexity | Status
Sprint 1-2 | F1 | F1-S1 | Project Structure & Configuration | P0 |  | Backlog
Sprint 1-2 | F1 | F1-S2 | Database Layer with PostgreSQL | P0 |  | Backlog
Sprint 1-2 | F1 | F1-S3 | MetIQ Enterprise AI Platform Integration | P0 |  | Backlog
Sprint 1-2 | F1 | F1-S4 | Embedding Client for Vector Search | P0 |  | Backlog
Sprint 1-2 | F1 | F1-S5 | Test Infrastructure | P0 |  | Backlog
Sprint 2-3 | F2 | F2-S1 | Define Workflow State Schema | P0 |  | Backlog
Sprint 2-3 | F2 | F2-S2 | Build Workflow Graph | P0 |  | Backlog
Sprint 2-3 | F2 | F2-S3 | Implement Routing Logic | P0 |  | Backlog
Sprint 2-3 | F2 | F2-S4 | Workflow Runner with Tracing | P0 |  | Backlog
Sprint 3-4 | F3 | F3-S1 | Base Agent Framework | P0 |  | Backlog
Sprint 3-4 | F3 | F3-S2 | Incident Deduplication | P0 |  | Backlog
Sprint 3-4 | F3 | F3-S3 | Error Classification | P0 |  | Backlog
Sprint 3-4 | F3 | F3-S4 | Correlation Analysis | P0 |  | Backlog
Sprint 3-4 | F3 | F3-S5 | Triage Agent Implementation | P0 |  | Backlog
Sprint 4-5 | F4 | F4-S1 | Knowledge Retrieval (RAG) | P0 |  | Backlog
Sprint 4-5 | F4 | F4-S2 | Hypothesis Generation | P0 |  | Backlog
Sprint 4-5 | F4 | F4-S3 | Evidence Gathering with Tools | P0 |  | Backlog
Sprint 4-5 | F4 | F4-S4 | Root Cause Synthesis | P0 |  | Backlog
Sprint 4-5 | F4 | F4-S5 | Diagnosis Agent Implementation | P0 |  | Backlog
Sprint 5-6 | F5 | F5-S1 | Tool Base Classes | P0 |  | Backlog
Sprint 5-6 | F5 | F5-S2 | Tool Registry | P0 |  | Backlog
Sprint 5-6 | F5 | F5-S3 | Rollback Manager | P0 |  | Backlog
Sprint 5-6 | F5 | F5-S4 | Proposal Agent | P0 |  | Backlog
Sprint 5-6 | F5 | F5-S5 | Execution Agent | P0 |  | Backlog
Sprint 5-6 | F5 | F5-S6 | Verification Agent | P0 |  | Backlog
Sprint 6-7 | F6 | F6-S1 | Provider Base Interface | P0 |  | Backlog
Sprint 6-7 | F6 | F6-S2 | SQL Server Provider | P0 |  | Backlog
Sprint 6-7 | F6 | F6-S3 | SQL Server Diagnostic Tools | P0 |  | Backlog
Sprint 6-7 | F6 | F6-S4 | SQL Server Remediation Tools | P0 |  | Backlog
Sprint 7-8 | F7 | F7-S1 | Vector Store with Azure AI Search | P1 |  | Backlog
Sprint 7-8 | F7 | F7-S2 | Known Error Database (KEDB) | P1 |  | Backlog
Sprint 7-8 | F7 | F7-S3 | Incident History for Learning | P1 |  | Backlog
Sprint 7-8 | F7 | F7-S4 | Howdy Integration for Historical Ticket Search | P1 |  | Backlog
Sprint 8-9 | F8 | F8-S1 | Structured Logging | P1 |  | Backlog
Sprint 8-9 | F8 | F8-S2 | Prometheus Metrics | P1 |  | Backlog
Sprint 8-9 | F8 | F8-S3 | LangSmith Integration | P1 |  | Backlog
Sprint 8-9 | F8 | F8-S4 | Audit Trail | P1 |  | Backlog
Sprint 9-10 | F9 | F9-S1 | FastAPI Application | P1 |  | Backlog
Sprint 9-10 | F9 | F9-S2 | Incident Endpoints | P1 |  | Backlog
Sprint 9-10 | F9 | F9-S3 | Health & Metrics Endpoints | P1 |  | Backlog
Sprint 9-10 | F9 | F9-S4 | API Authentication | P1 |  | Backlog
Sprint 9-10 | F9 | F9-S5 | Azure Service Bus Integration | P1 |  | Backlog
Sprint 9-10 | F9 | F9-S6 | SCSM ITSM Integration | P1 |  | Backlog
Sprint 10-11 | F10 | F10-S1 | Approval Request System | P1 |  | Backlog
Sprint 10-11 | F10 | F10-S2 | Approval API Endpoints | P1 |  | Backlog
Sprint 10-11 | F10 | F10-S3 | Auto-Approval Rules | P1 |  | Backlog
Sprint 11-12 | F11 | F11-S1 | Notification Channels | P2 |  | Backlog
Sprint 11-12 | F11 | F11-S2 | Escalation Logic | P2 |  | Backlog
Sprint 11-12 | F11 | F11-S3 | Ticket Creation with SCSM | P2 |  | Backlog
Sprint 12+ | F12 | F12-S1 | Dashboard API | P2 |  | Backlog
Sprint 12+ | F12 | F12-S2 | Reporting Endpoints | P2 |  | Backlog